## RMS
Function/Screen | Feature | Sub Feature | Level* | User Role1 | User Role2 | .. | Description | Planned | In Charge | Done | Status | Status Notes | RDS | Updated | Update Details
Home Page | Common |  | Medium | x | x | x | <<brief description of the screen>> | Iteration 1 | HaTH | Iteration 1 | To Do |  | II.1.3, III.5 | Not Yet
User Login | Common |  | Simple |  |  |  | Use Cases: - Login System | Iteration 1 | KienNT | Iteration 2 | To Do |  | II.2.1; III.1.1.a | Not Yet
User Register | Common |  | Simple |  |  |  | .. | Iteration 1 | AnhPT | Iteration 2 | To Do |  |  | Not Yet
Reset Password | Common |  | Medium |  |  |  | .. | Iteration 1 | AnhPT | Iteration 1 | To Do |  |  | Iteration 2
User Authorization | Common |  | Complex |  |  |  | .. | Iteration 2 | TuanNV | Iteration 2 | To Do |  |  | Iteration 3
User Profile | Common |  | Simple |  |  |  | .. | Iteration 3 | ThuyTT | Iteration 3 | To Do |  |  | Not Yet
Change Password | Common |  | Simple |  |  |  | .. | Iteration 2 | KienNT | Iteration 2 | To Do |  |  | Not Yet
Blogs List | Public |  | Medium |  |  |  | .. | Iteration 2 | HaTH | Iteration 2 | To Do |  |  | Not Yet
Blog Details | Public |  | Simple |  |  |  | .. | Iteration 3 | AnhPT | Iteration 3 | To Do |  |  | Not Yet
Posts List | Marketing |  | Medium |  |  |  | .. | Iteration 2 | HaTH | Iteration 2 | To Do |  |  | Not Yet
Post Details | Marketing |  | Medium |  |  |  | .. | Iteration 2 | KienNT | Iteration 3 | To Do |  |  | Not Yet
Users List | System Admin |  | Simple |  |  |  | .. | Iteration 3 | TuanNV | Iteration 3 | To Do |  |  | Not Yet
User Details | System Admin |  | Simple |  |  |  | .. | Iteration 3 | ThuyTT | Iteration 3 | To Do |  |  | Not Yet
(*) You can rate the functions' complexity level based on the number of fields on the screens or the number of transactions in the function, with the details as below
Simple: <=7 fields OR <=3 transactions
Medium: <=15 fields OR <= 7 transactions
Complex: >15 fields OR > 7 transactions
In which:
fields: screen components or database table fields
transactions can be counted actioning UI components, user or database access transactions
f
Note on L1: kiennt: IT~Function Integration and Integration Test
Note on N1: KienNT: The name of section in the RDS (requirement and design specification) document

## Iter1
# | Screen / Function | In Charge | Status | Notes
1 | Screen/Function Name1 | KienNT | To Do
2 | Screen/Function Name2 | VinhLX | To Do
Note on D1: kiennt: IT~Function Integration and Integration Test

## Iter2
# | Screen / Function | In Charge | Status | Notes
1 | Screen/Function Name1 | KienNT | To Do
2 | Screen/Function Name2 | VinhLX | To Do
Note on D1: kiennt: IT~Function Integration and Integration Test

## Iter3
# | Screen / Function | In Charge | Status | Notes
1 | Screen/Function Name1 | KienNT | To Do
2 | Screen/Function Name2 | VinhLX | To Do
Note on D1: kiennt: IT~Function Integration and Integration Test